## Sheet1
Question | A | B | C | D | Answer
At the eighth Sprint Review, the stakeholders are upset that the product being built is not what they expected and will incur additional costs that were not planned for. What may have led to this? (Choose the best answer) | The Scrum Master has not been reporting on the progress of the Scrum team. The Product Owner has not been managing the tasks of the Developers effectively. The Developers have not been improving their velocity. | The project's transparency has not been ensured by the Scrum Master. The project's progress has not been communicated to the stakeholders by the Product Owner. The Sprint Reviews have not been attended by the stakeholders. | The Scrum Master has not been attending the Daily Standup. The Product Owner has not been using the Gantt chart correctly. The stakeholders have not been invited to the Sprint Retrospectives. | None | B
If burndown charts are used to visualize progress, what does a trendline through a release burndown chart indicate? (Choose the best answer) | When all work will be completed so the Scrum team can start working on a new Product Backlog. | When the project will be over if the Product Owner removes work that is equal in effort to any new work that is added. | When the work remaining is projected to be completed if nothing changes on the Product Backlog or Developers'. | The evolution of the return of investment on the project. | C
Steven is a Scrum Master on a new Scrum team. What would be the best way for him to determine if the Product Owner is interacting enough with the Developers during a Sprint? (Choose the best answer) | Check whether the Product Owner is actively engaged at the Daily Scrums. | Check whether the Increment presented at the Sprint Review meets the Product Owner’s expectations. | Observe whether the Product Owner has provided enough information at the Sprint Planning to make his/ her presence optional during the Sprint. The level of autonomy within the Developers can be the result of having the right presence from the Product Owner. | he Product Owner must be present at all times when the Developers are working. Scrum forbids the Product Owner from being unavailable. | B
After several Sprints, a key stakeholder starts using the product. The stakeholders are surprised by the slow performance and complain to the Product Owner. The Product Owner comes to the Scrum Master asking for advice.What is the best course of action for a Scrum Master? (Choose the best answer) | Wait until the next Sprint Retrospective to change the Definition of Done because that is when it is most appropriate. | Bring the concern to the testers and ask them to include performance testing. | Explain to the Product Owner that it’s up to the Developers to decide on acceptable performance standards as they own the Definition of Done. | Encourage the Product Owner to bring any performance issues to the Developers' attention and collaborate with them on how to improve performance and, as a result, have a stronger Definition of Done. | D